## Training Plan
IQ | SQL Python Plan
The Display Week in cell E4 represents the starting week to display in the project schedule in cell I4. The project start date is considered Week 1. To change the display week, simply enter a new week number in cell E4. The starting date for each week, starting with the display week from cell E4, starts in cell I4 and is auto calculated. There are 8 weeks represented in this view from cell I4 through cell BF4. You should not modify these cells. Display Week: label is in cell C4. |  | Project Start: |  | 2022-07-05 |  |  |  | 2022-07-04 | [6 empty] | 2022-07-11 | [6 empty] | 2022-07-18 | [6 empty] | 2022-07-25 | [6 empty] | 2022-08-01 | [6 empty] | 2022-08-08 | [6 empty] | 2022-08-15 | [6 empty] | 2022-08-22
Cells I5 through BL5 contain the day number for the week represented in the cell block above each date cell and are auto calculated. You should not modify these cells. Today's date is outlined in Red (hex #AD3815) from today's date in row 5 through the entire date column to the end of the project schedule. |  | Display Week: |  | 1 | time axis 2022-07-04 to 2022-08-28
This row contains headers for the project schedule that follows below them. Navigate from B6 through BL 6 to hear the content. The first letter of each day of the week for the date above that heading, starts in cell I6 and continues through cell BL6. All project timeline charting is auto generated based on the start and end dates entered, using conditional formats. Do not modify content in cells within columns after column I starting with cell I7. | TASK | ASSIGNED TO | PROGRESS | START | END |  | DAYS | time axis 2022-07-04 to 2022-08-28
Do not delete this row. This row is hidden to preserve a formula that is used to highlight the curren day within the project schedule.
Cell B8 contains the Phase 1 sample title. Enter a new Title in cell B8. Enter a name to assign the phase to, if it applies for your project, in cell C8. Enter Progress for the entire phase, if it applies for your project, in cell D8. Enter the start and end dates for the entire phase, if it applies for your project, in cells E8 and F8. The Gantt chart will automatically fill in the appropriate dates and shade according to the progress entered. To delete the phase and work only from tasks, simply delete this row. | Sql Basic
| select order till slide 7 | Vinod | 0% | 2022-07-05 | 2022-07-05
Rows 10 through 13 repeat the pattern from row 9. Repeat the instructions from cell A9 for all task rows in this worksheet. Overwrite any sample data. A sample of another phase starts in cell A14. Continue entering tasks in cells A10 through A13 or go to cell A14 to learn more. | top operatior till slide 15 | Vinod | 0% | 2022-07-06 | 2022-07-06 | 2 | 1
| Insert update delete till slide 29 | Vinod | 0% | 2022-07-07 | 2022-07-07
| data type and in built function till slide 43 | Vinod | 0% | 2022-07-08 | 2022-07-08
| join alter till slide 65 | Vinod | 0% | 2022-07-11 | 2022-07-11
| Finished basic concept on SQL | Vinod | 0% | 2022-07-12 | 2022-07-12 | 5 | 1
Sample phase title block | Sql intermediate
| Completed full ppt | Vinod | 0% | 2022-07-13 | 2022-07-13 | 1 | 1
Sample phase title block | Sql Advanced
| 25 slide finished | Vinod | 0% | 2022-07-14 | 2022-07-14 | 1 | 1
| full advance sesson 17 slide completed | Vinod | 0% | 2022-07-15 | 2022-07-15 | 2 | 1
The cell at right contains the Phase 2 sample title. You can create a new phase at any time within column B. This project schedule does not require phases. To remove the phase, simply delete the row. To create a new phase block in this row, enter a new Title in cell at right. To continue adding tasks to the phase above, enter a new row above this one and fill in the task data as in cell A9's instruction. Update the Phase details in cell at right based on cell A8's instruction. Continue navigating down column A cells to learn more. If you haven't added any new rows in this worksheet, you will find 2 additional sample phase blocks have been created for you in cells B20 and B26. Otherwise, navigate through column A cells to find the additional blocks. Repeat the instructions from cells A8 and A9 whenever you need to. | Python Basic
| Basic python discussed during first session | Vinod | 0% | 2022-07-18 | 2022-07-18
| Panadas dataframe exploration | Vinod |  | 2022-07-19 | 2022-07-19
| Dataframe cleaning and handling missing values | Vinod | 0% | 2022-07-20 | 2022-07-20 | 2 | 1
| Python Extented lab session | Vinod | 0% | 2022-07-21 | 2022-07-21 | 3 | 1
Sample phase title block | Python Intermediate
| Matplot lib and seaborn library | Vinod | 0% | 2022-07-22 | 2022-07-22 | 1 | 1
| Numpy Library Discussion | Vinod | 0% | 2022-07-25 | 2022-07-25 | 2 | 1
Python Advanced
| Oops concept | Vinod | 0% | 2022-07-26 | 2022-07-26 | 1 | 1
| Realtime python problem project wise | Vinod | 0% | 2022-07-27 | 2022-07-29 | 5 | 3

## NIT New Joiners
Employee | Python(Self) | Sql(Self) | Python | Sql | Story boarding | Analytical | communication | Presentation | Technical Score | Professional Score
Dhanush Kumaran | 6 | 8 | 3 | 4 | 1 | 1 | 4 | 1 | 7 | 7
Dias Xavy | 4 | 7 | 4 | 4 |  |  |  |  | 8 | 0
Divyanshu Bajpai | 7 | 8 | 3 | 3 | 1 | 2 | 2 | 2 | 6 | 7
Giridhar Naidu | 5 | 7 | 3 | 4 | 2 | 3 | 4 | 3 | 7 | 12
Karan Singh | 7 | 7 | 3 | 3 |  |  |  |  | 6 | 0
Perikala Pradeep | 7 | 9 | 3 | 4 |  |  |  |  | 7 | 0
Sainath Gadgeppa | 8 | 8 | 3 | 4 | 2 | 2 | 3 | 2 | 7 | 9
Satheeshkumar M | 6.5 | 8.5 | 5 | 6 |  |  |  |  | 11 | 0
Saurav Shukla | 8 | 6 | 6 | 5 | 4 | 4 | 3 | 4 | 11 | 15
Shivam Sinha | 6 | 7 | 5 | 8 | 5 | 5 | 4 | 4 | 13 | 18
Tharun Kumar | 3 | 7 | 3 | 4 | 4 | 5 | 3 | 3 | 7 | 15
Vishnu Bandaru | 6 | 7 | 5 | 5 | 0 | 1 | 3 | 1 | 10 | 5
Ajay Nujella | 6.5 | 7 | 4 | 4 | 3 | 3 | 4 | 3 | 8 | 13
Yogesh Tiwari | 6 | 8 | 4 | 5 | 2 | 3 | 4 | 2 | 9 | 11
Santosh Parmar | 4.5 | 7 | 3 | 4 |  |  |  |  | 7 | 0
Aswin S C |  | 8 | 4 | 6 | 2 | 2 | 4 | 2 | 10 | 10
S Rohit | 7 | 7 | 3 | 5 |  |  |  |  | 8 | 0
Dhananjay Nandeshwar | 7 | 7 | 3 | 4 |  |  |  |  | 7 | 0
Akash Dighade | 7 | 7 | 4 | 4 |  |  |  |  | 8 | 0
Shivani Kishor | 6.5 | 7.5 | 3 | 4 | 4 | 3 | 4 | 4 | 7 | 15
Srinidhi | 6 | 7 | 3 | 4 | 3 | 4 | 4 | 4 | 7 | 15
Lakshya Agarwal | 10 | 8 | 4 | 3 | 3 | 4 | 5 | 4 | 7 | 16
Raamesh B | 6 | 8 | 4 | 4 |  |  |  |  | 8 | 0
M Vijay | 8 | 10 | 4 | 3 |  |  |  |  | 7 | 0

## Fico Hours Planning
500
Hours | Pravin | Sumit | Varsha | Anuja | Vinod | Satyam | Anand
Jan | 160 | 160 | 40 | 20 | 60
Feb | 160 | 160 | 40 | 20 | 60
Mar | 160 | 160 | 40 | 20 | 20
Apr | 160 | 160 | 40 | 20 | 20
May | 160 | 160 | 40 | 20 | 20
Jun | 160 | 160 | 40 | 20 | 20
Jul | 160 | 160 | 40 | 20 | 20
Aug | 160 | 160 | 40 | 20 | 40 | 80 | 80 | Migration from sftp to C-scan,QC and parallel run
Sep | 80 | 80 | 20 | 10 | 10 | 80 | 80
Oct | 120 | 120 | 20 | 10 | 10 | 80 | 80
Nov | 120 | 120 | 20 | 10 | 10
Dec | 120 | 120 | 20 | 10 | 10
Total | 1720 | 1720 | 400 | 200 | 300 | 240 | 240
PM | 500 | 900 | 400
SA-Dev | 500
SA-M | 1500
| 2000 | 3920 | 1920